## Control Overview
Control ID | Control Name | Category | Difficulty | Prerequisites | Control Description | Artifacts{Documents, Logs, Diagrams, Images, Video} | Comments
5.1 | Policies for information security | Organizational | 2 | None - Foundational | Information security policy and topic-specific policies shall be defined approved by management published communicated to and acknowledged by relevant personnel and relevant interested parties and reviewed at planned intervals and if significant changes occur | Documents | Often will be included as part of an employment contract.
5.2 | Information security roles and responsibilities | Organizational | 2 | None - Foundational | Information security roles and responsibilities shall be defined and allocated according to the organization needs | Documents, Diagrams
5.3 | Segregation of duties | Organizational | 2 | 5.1 (Policy); 5.2 (Roles) | Conflicting duties and conflicting areas of responsibility shall be segregated | Images | Generally showing change controls to production is "good enough", GitHub / GetLab
5.4 | Management responsibilities | Organizational | 2 | 5.1 (Policy); 5.2 (Roles) | Management shall require all personnel to apply information security in accordance with the established information security policy topic-specific policies and procedures of the organization | Documents | -
5.5 | Contact with authorities | Organizational | 1 | 5.1 (Policy); 5.2 (Roles) | The organization shall establish and maintain contact with relevant authorities | Documents | -
5.6 | Contact with special interest groups | Organizational | 1 | 5.1 (Policy); 5.2 (Roles) | The organization shall establish and maintain contact with special interest groups or other specialist security forums and professional associations | Documents, Images | -
5.7 | Threat intelligence | Organizational | 1 | 5.1 (Policy); 5.2 (Roles) | Information relating to information security threats shall be collected and analyzed to produce threat intelligence | Documents, Images | Crowdstrike Screenshot of Sample Evidence (get from website / trial)
5.8 | Information security in project management | Organizational | 5 | 5.1 (Policy); 5.2 (Roles) | Information security shall be integrated into project management | Documents | Data Enablement Program (How do changes to the enterprise affect the security and availability of data?). Find a project security risk assessment.
5.9 | Inventory of information and other associated assets | Organizational | P | 5.1 (Policy); 5.2 (Roles) | An inventory of information and other associated assets including owners shall be developed and maintained | Documents | -
5.10 | Acceptable use of information and other associated assets | Organizational | 1 | 5.1 (Policy); 5.2 (Roles) | Rules for the acceptable use and procedures for handling information and other associated assets shall be identified documented and implemented | Documents, Logs, Images | Look at NIST
5.11 | Return of assets | Organizational | P | 5.1 (Policy); 5.2 (Roles) | Personnel and other interested parties as appropriate shall return all the organization's assets in their possession upon change or termination of their employment contract or agreement | Documents, Logs | Generate a list of terminated users over the audit period. Receipt of laptops being returned (UPS / Warehouse etc.)
5.12 | Classification of information | Organizational | 2 | 5.1 (Policy); 5.2 (Roles) | Information shall be classified according to the information security requirements based on confidentiality integrity availability and relevant interested party requirements | Documents | Information Classification Policy, Inventory of Data Types and their classification.
5.13 | Labelling of information | Organizational | 4 | 5.1 (Policy); 5.2 (Roles) | An appropriate set of procedures for information labelling shall be developed and implemented in accordance with the information classification scheme adopted by the organization | Documents, Images | Labeling in cloud is easy, retrofitting onprem can be very hard.
5.14 | Information transfer | Organizational | 1 | 5.1 (Policy); 5.2 (Roles) | Information transfer rules procedures or agreements shall be in place for all types of transfer facilities within the organization and between the organization and other parties | Documents | Data encryption standard should be included in the Information Classification Policy.
5.15 | Access control | Organizational | 2 | 5.1 (Policy); 5.2 (Roles) | Rules to control physical and logical access to information and other associated assets shall be established and implemented based on business and information security requirements | Logs, Images | VPNs / Bastion Host to access sensitive data.
5.16 | Identity management | Organizational | 2 | 5.1 (Policy); 5.2 (Roles) | The full life cycle of identities shall be managed | Documents, Logs, Images | On Boarding / Off Boarding
5.17 | Authentication information | Organizational | 2 | 5.1 (Policy); 5.2 (Roles) | Allocation and management of authentication information shall be controlled by a management process including advising personnel on appropriate handling of authentication information | Documents | Security Training Records / Active Directory LDAP Export
5.18 | Access rights | Organizational | 2 | 5.1 (Policy); 5.2 (Roles) | Access rights to information and other associated assets shall be provisioned removed and reviewed in accordance with the organization's topic-specific policy on and procedures for access control | Documents, Logs, Diagrams | On-Boarding / Access Review
5.19 | Information security in supplier relationships | Supplier | 3 | 5.1 (Policy); 5.2 (Roles) | Processes and procedures shall be defined and implemented to manage the information security risks associated with the use of supplier's products or services | Documents | Really we need a vendor assurance report (e.g. ISO 27001 / SOC etc.) on a company to fulfill this requirement.
5.20 | Addressing information security within supplier agreements | Supplier | 2 | 5.1 (Policy); 5.2 (Roles) | Relevant information security requirements shall be established and agreed with each supplier based on the type of supplier relationship | Documents | Vendor Contract or service agreement that specifies information security requirements.
5.21 | Managing information security in the ICT supply chain | Supplier | 4 | 5.1 (Policy); 5.2 (Roles) | Processes and procedures shall be defined and implemented to manage the information security risks associated with the ICT products and services supply chain | Documents | Risk committee assement for onboarding vendors followed by a yearly assessment. If a vendor goes out of business the risk is the cost associated with switching to another vendor.
5.22 | Monitoring review and change management of supplier services | Supplier | 4 | 5.1 (Policy); 5.2 (Roles) | The organization shall regularly monitor review audit and manage changes to supplier's information security practices and service delivery | Documents | Annual review of 5-21, can be accomplished with a security questionnaire.
5.23 | Information security for use of cloud services | Organizational | 4 | 5.1 (Policy); 5.2 (Roles) | Processes for acquisition use management and exit from cloud services shall be established in accordance with the organization's information security requirements | Documents | TWR
5.24 | Information security incident management planning and preparation | Organizational | 2 | 5.1 (Policy); 5.2 (Roles) | The organization shall plan and prepare for managing information security incidents by defining establishing and communicating information security incident management processes procedures and responsibilities | Documents | NIST SP 800-61r3
5.25 | Assessment and decision on information security events | Organizational | 2 | 5.1 (Policy); 5.2 (Roles) | The organization shall assess information security events and decide if they are to be categorized as information security incidents | Logs, Images | Need to show how incidents are monitored and processed. (AWS Guard Duty, Microsoft Sentinel, SIEM Logs)
5.26 | Response to information security incidents | Organizational | 1 | 5.1 (Policy); 5.2 (Roles) | Information security incidents shall be responded to in accordance with the documented procedures | Documents | Need a list of incidents / ticket system and how they were mitigated. Generated a NIST SP 800-61r3 compliant incident report using Sonnet4
5.27 | Learning from information security incidents | Organizational | 1 | 5.1 (Policy); 5.2 (Roles) | Knowledge gained from information security incidents shall be used to strengthen and improve the information security controls | Documents | Generated a NIST SP 800-61r3 compliant incident report using Sonnet4
5.28 | Collection of evidence | Organizational | 2 | 5.1 (Policy); 5.2 (Roles) | The organization shall establish and implement procedures for the identification collection acquisition and preservation of evidence related to information security events | Logs | Logs like firewall logs with poof that the logs cannot be modified (immutable).
5.29 | Information security during disruption | Organizational | 1 | 5.1 (Policy); 5.2 (Roles) | The organization shall plan how to maintain information security at an appropriate level during disruption | Documents | Generated a NIST SP 800-34r1 compliant BCP using Sonnet4
5.30 | ICT readiness for business continuity | Organizational | 1 | 5.1 (Policy); 5.2 (Roles) | ICT readiness shall be planned implemented maintained and tested based on business continuity objectives and ICT continuity requirements | Documents | BCP Should be tested.
5.31 | Legal and contractual requirements | Organizational | 4 | 5.1 (Policy); 5.2 (Roles) | Legal statutory regulatory and contractual requirements relevant to information security and the organization's approach to meet these requirements shall be identified documented and kept up to date | Documents | Either have legal show the process they follow OR provide a sample contract.
5.32 | Intellectual property rights | Organizational | 3 | 5.1 (Policy); 5.2 (Roles) | The organization shall implement appropriate procedures to protect intellectual property rights | Documents | Documented procedure which is created by legal and approved by management.
5.33 | Protection of records | Organizational | 3 | 5.1 (Policy); 5.2 (Roles) | Records shall be protected from loss destruction falsification unauthorized access and unauthorized release | Documents, Logs, Images | Need to show what users have access to production data and servers. Need encrypted backups that are immutable. Encrypted data at rest. Data disposal policy. If it is on the cloud then this is a really easy control to meet.
5.34 | Privacy and protection of personal information | Organizational | 4 | 5.1 (Policy); 5.2 (Roles) | The organization shall identify and meet the requirements regarding privacy and protection of PII according to applicable laws and regulations and contractual requirements | Documents | Does the company have PII? If no {then skip}. If yes then they need to show what data they collect and how they are protecting it. Consider: PHI, PII, PCI DSS, Financial Transactions (Tax returns)
5.35 | Independent review of information security | Organizational | 4 | 5.1 (Policy); 5.2 (Roles) | The organization's approach to managing information security and its implementation including people processes and technologies shall be reviewed independently at planned intervals or when significant changes occur | Documents | Company should have an internal independent audit team.
5.36 | Compliance with policies and standards for information security | Organizational | 3 | 5.1 (Policy); 5.2 (Roles) | Compliance with the organization's information security policy topic-specific policies rules and standards shall be regularly reviewed | Documents | Documented internal review of information security policies and procedures annually.
5.37 | Documented operating procedures | Organizational | 3 | 5.1 (Policy); 5.2 (Roles) | Operating procedures for information processing facilities shall be documented and made available to personnel who need them | Documents | Generate with LLM.
6.1 | Screening | People | 3 | 5.x controls; Access controls (5.15-5.18) | Background verification checks on all candidates to become personnel shall be carried out prior to joining the organization and on an ongoing basis in accordance with relevant laws regulations ethics and proportional to the business requirements the classification of the information to be accessed and the perceived risks | Documents | Generate background checks
6.2 | Terms and conditions of employment | People | 2 | 5.x controls; Access controls (5.15-5.18) | The employment contractual agreements shall state the personnel's and the organization's responsibilities for information security | Documents | Signed employee agreement
6.3 | Information security awareness education and training | People | 3 | 5.x controls; Access controls (5.15-5.18) | Personnel of the organization and relevant interested parties shall receive appropriate information security awareness education and training and regular updates of the organization's information security policy topic-specific policies and procedures as relevant for their job function | Documents | Onboarding training
6.4 | Disciplinary process | People | 3 | 5.x controls; Access controls (5.15-5.18) | A disciplinary process shall be formalized and communicated to take actions against personnel and other relevant interested parties who have committed an information security policy violation | Documents, Images | Three strike policy
6.5 | Responsibilities after termination or change of employment | People | 3 | 5.x controls; Access controls (5.15-5.18) | Information security responsibilities and duties that remain valid after termination or change of employment shall be defined enforced and communicated to relevant personnel and other interested parties | Documents | Should be part of employment contract.
6.6 | Confidentiality or non-disclosure agreements | People | 3 | 5.x controls; Access controls (5.15-5.18) | Confidentiality or non-disclosure agreements reflecting the organization's needs for the protection of information shall be identified documented regularly reviewed and signed by personnel and other relevant interested parties | Documents | Should be part of employment contract.
6.7 | Remote working | People | 2 | 5.x controls; Access controls (5.15-5.18) | Security measures shall be implemented when personnel are working remotely to protect information accessed processed or stored outside the organization's premises | Documents, Diagrams, Images | Remote employees should use VPN for access. Remote access VPN logs.
6.8 | Information security event reporting | People | 3 | 5.x controls; Access controls (5.15-5.18) | The organization shall provide a mechanism for personnel to report observed or suspected information security events through appropriate channels in a timely manner | Images | Internal portal for employees to remote incidents. Should be communicated as part of the onboarding training.
7.1 | Physical security perimeters | Physical | 2 | 5.x controls; Asset management (5.9) | Security perimeters shall be defined and used to protect areas that contain information and other associated assets | Documents, Diagrams | Data center security, Generate from NIST SP 800-100
7.2 | Physical entry | Physical | 3 | 5.x controls; Asset management (5.9) | Secure areas shall be protected by appropriate entry controls and access points to ensure that only authorized personnel are allowed access | Documents, Diagrams | Access control systems for office, Generate from NIST IR 7316
7.3 | Securing offices rooms and facilities | Physical | 4 | 5.x controls; Asset management (5.9) | Physical security for offices rooms and facilities shall be designed and implemented | Documents, Diagrams, Images | -
7.4 | Physical security monitoring | Physical | 2 | 5.x controls; Asset management (5.9) | Premises shall be continuously monitored for unauthorized physical access | Documents, Images | -
7.5 | Protecting against physical and environmental threats | Physical | 2 | 5.x controls; Asset management (5.9) | Protection against physical and environmental threats shall be designed and implemented | Documents | -
7.6 | Working in secure areas | Physical | 2 | 5.x controls; Asset management (5.9) | Security measures for working in secure areas shall be designed and implemented | Documents, Images | -
7.7 | Clear desk and clear screen | Physical | 3 | 5.x controls; Asset management (5.9) | Clear desk rules for papers and removable storage media and clear screen rules for information processing facilities shall be defined and appropriately enforced | Documents, Video | Get a copy of Office Space and a few Episodes of The Office and test GPT's ability to detect clean desks and locked computers.
7.8 | Equipment siting and protection | Physical | 4 | 5.x controls; Asset management (5.9) | Equipment shall be sited and protected to reduce the risks from environmental threats and hazards and opportunities for unauthorized access | Documents, Images | -
7.9 | Security of assets off-premises | Physical | 2 | 5.x controls; Asset management (5.9) | Off-site assets shall be protected | Documents, Images | Document of policy, image of locks
7.10 | Storage media | Physical | P | 5.x controls; Asset management (5.9) | Storage media shall be managed through their life cycle of acquisition use transport and disposal in accordance with the organization's classification scheme and handling requirements | Documents, Images | Spreadsheet of the asset lifecycle, decommissioning and certificate of destruction for Eo (Panteah)
7.11 | Supporting utilities | Physical | 3 | 5.x controls; Asset management (5.9) | Information processing facilities shall be protected from power failures and other disruptions caused by failures in supporting utilities | Documents | Either a datacenter service agreement or process/procedures to prevent power failures/access to backup generators.
7.12 | Cabling security | Physical | 3 | 5.x controls; Asset management (5.9) | Cables carrying power data or supporting information services shall be protected from interception interference or damage | Documents, Images | Either a datacenter service agreement, or pictures of the cables being protected.
7.13 | Equipment maintenance | Physical | 2 | 5.x controls; Asset management (5.9) | Equipment shall be maintained correctly to ensure availability integrity and confidentiality of information | Documents | Quarterly equipment service checklists.
7.14 | Secure disposal or re-use of equipment | Physical | P | 5.x controls; Asset management (5.9) | Items of equipment containing storage media shall be verified to ensure that any sensitive data and licensed software has been removed or securely overwritten prior to disposal or re-use | Documents | Secure overwrite prior to destruction
8.1 | User endpoint devices | Technology | 2 | 5.x controls; Access controls; Monitoring (8.16) | Information stored on processed by or accessible via user endpoint devices shall be protected | Documents, Images | Endpoint security policy, Screenshot of MDM
8.2 | Privileged access rights | Technology | 2 | 5.x controls; Access controls; Monitoring (8.16) | The allocation and use of privileged access rights shall be restricted and managed | Documents | Annual review of privileged access list. Need to generate a checklist and show a history of them (Quarterly is generally good enough)
8.3 | Information access restriction | Technology | 3 | 5.x controls; Access controls; Monitoring (8.16) | Access to information and other associated assets shall be restricted in accordance with the established topic-specific policy on access control | Documents, Images | Who has access to databases? What kind of data do they have access to? Screenshot of the database access list and justification for why they have access. Different scenario for internal vs SaaS applications.
8.4 | Access to source code | Technology | 1 | 5.x controls; Access controls; Monitoring (8.16) | Read and write access to source code program libraries and related items shall be appropriately managed | Documents, Images | Who has access to code. Screenshot of code access list (e.g. GitHub / GitLab) and justification of why they have access.
8.5 | Secure authentication | Technology | ? | 5.x controls; Access controls; Monitoring (8.16) | Secure authentication technologies and procedures shall be implemented based on information access restrictions and the topic-specific policy on access control | Images | Proof that encryption is being used (TLS, SFTP, VPN etc.). Find / create screenshots.
8.6 | Capacity management | Technology | 2 | 5.x controls; Access controls; Monitoring (8.16) | The use of resources shall be monitored and adjusted in line with current and expected capacity requirements to ensure the required system performance | Documents, Images | Cloud auto scaling OR Plan for capacity expansion based on need (like on blackfriday)
8.7 | Protection against malware | Technology | 2 | 5.x controls; Access controls; Monitoring (8.16) | Protection against malware shall be implemented and supported by appropriate user awareness | Logs | Anti-virus logs
8.8 | Management of technical vulnerabilities | Technology | 2 | 5.x controls; Access controls; Monitoring (8.16) | Information about technical vulnerabilities of information systems in use shall be obtained the organization's exposure to such vulnerabilities shall be evaluated and appropriate measures shall be taken | Documents | Need vulnerability scans and Application Security Scans. Penetration testing report.
8.9 | Configuration management | Technology | 4 | 5.x controls; Access controls; Monitoring (8.16) | Configurations including security configurations of hardware software services and networks shall be established documented implemented monitored and reviewed | Documents, Images | Need to provide server configuration baselines (OS Hardening. anti-virus installed, ports closed, etc.) with a ticketing system for controlling change control process approval chain.
8.10 | Information deletion | Technology | 3 | 5.x controls; Access controls; Monitoring (8.16) | Information stored in information systems databases and records shall be deleted when no longer required | Documents, Logs | Does the company have PII? If no {then skip}. If yes then they need to show what data they collect and proof of adherence to retention requirements. Consider: PHI, PII, PCI DSS, Financial Transactions (Tax returns)
8.11 | Data masking | Technology | 1 | 5.x controls; Access controls; Monitoring (8.16) | Data masking shall be used in accordance with the organization's topic-specific policy on access control and other related topic-specific policies and business requirements taking applicable legislation into consideration | Images | Screenshot proof that passwords are hidden when being entered by *******
8.12 | Data leakage prevention | Technology | 2 | 5.x controls; Access controls; Monitoring (8.16) | Data leakage prevention measures shall be applied to systems networks and any other devices that process store or transmit sensitive information | Images | Find a DLP configuration policy (find YouTube video of how they are being setup, take a screenshot).
8.13 | Information backup | Technology | 2 | 5.x controls; Access controls; Monitoring (8.16) | Backup copies of information software and systems shall be maintained and regularly tested in accordance with the agreed topic-specific policy on backup | Documents | Generate a backup policy. Take a screenshot of a YouTube video of configuring backup solutions. Log of Backup test and the result of said test.
8.14 | Redundancy of information processing facilities | Technology | 3 | 5.x controls; Access controls; Monitoring (8.16) | Information processing facilities shall be implemented with redundancy sufficient to meet availability requirements | Diagrams, Images | Need alert generation to notify if capacity is exceeding 80%. If it is in cloud then need to use dynamic capacity expansion. Architectural diagram showing redundant switches, firewalls, servers (for onprem).
8.15 | Logging | Technology | 2 | 5.x controls; Access controls; Monitoring (8.16) | Logs that record activities exceptions faults and other relevant events shall be produced stored protected and analyzed | Images | Proof that logs are being forwarded to a SIEM (take screenshot of YouTube video showing server is configured to forward logs). Very easy for cloud.
8.16 | Monitoring activities | Technology | 2 | 5.x controls; Access controls; Monitoring (8.16) | Networks systems and applications shall be monitored for anomalous behavior and appropriate actions taken to evaluate potential information security incidents | Images | Find a SIEM configuration YouTube video of how they are being setup, take a screenshot.
8.17 | Clock synchronization | Technology | 1 | 5.x controls; Access controls; Monitoring (8.16) | The clocks of information processing systems within the organization or security domain shall be synchronized to approved time sources | Images | Screenshot of windows begin configured to use a NTP server.
8.18 | Use of privileged utility programs | Technology | 1 | 5.x controls; Access controls; Monitoring (8.16) | The use of utility programs that might be capable of overriding system and application controls shall be restricted and tightly controlled | Images | Provide AD screenshots.
8.19 | Installation of software on operational systems | Technology | 2 | 5.x controls; Access controls; Monitoring (8.16) | Procedures and measures shall be implemented to securely manage software installation on operational systems | Images | Need proof of software management tool for the organization.
8.20 | Networks security | Technology | 3 | 5.x controls; Access controls; Monitoring (8.16), 8.18 | Networks and network devices shall be secured managed and controlled to protect information in systems and applications | Images | Provide AD Group Policy configuration, AV Management Screenshot
8.21 | Security of network services | Technology | 4 | 5.x controls; Access controls; Monitoring (8.16) | Security mechanisms service levels and service requirements of network services shall be identified implemented and monitored | Documents, Diagrams, Images | Identify security caragory of network devices and catagorize them accordingly (e.g. PCI environment vs user LAN), SS of SIEM receiving logs / monitoring the system
8.22 | Segregation of networks | Technology | 3 | 5.x controls; Access controls; Monitoring (8.16) | Groups of information services users and information systems shall be segregated in the organization's networks | Documents, Diagrams, Images | Firewall Policy / ACLs OR Router Routes / vLAN configs, and network diagrams
8.23 | Web filtering | Technology | 3 | 5.x controls; Access controls; Monitoring (8.16) | Access to external websites shall be appropriately managed to reduce exposure to malicious content | Documents, Images | Application Firewall Configs OR Firewall Policy
8.24 | Use of cryptography | Technology | 4 | 5.x controls; Access controls; Monitoring (8.16) | Rules for the effective use of cryptography including cryptographic key management shall be defined and implemented | Documents, Images | Crypto Policy, Key Management/Store Configs
8.25 | Secure development life cycle | Technology | 3 | 5.x controls; Access controls; Monitoring (8.16) | Rules for the secure development of software and systems shall be established and applied | Documents | SDLC Secure Development Policy and Procedires Documents, SLDC Tickets to show that the policy is being followed.
8.26 | Application security requirements | Technology | 2 | 5.x controls; Access controls; Monitoring (8.16); Secure Development Life Cycle (8.25) | Information security requirements shall be identified, specified, and approved when developing or acquiring applications | Documents | Documets showing the process for identifying security requirements and how they adhear to the SDLC Sec Dev Policy
8.27 | Secure system architecture and engineering principles | Technology | 4 | 5.x controls; Access controls; Monitoring (8.16); Secure Development Life Cycle (8.25) | Principles for engineering secure systems shall be established, documented, maintained, and applied to any information system development activities | Documents | Policies and Procedures for minimal security standards (standard baseline configs, SDLC Sec Dev Policy, etc.)
8.28 | Secure coding | Technology | 3 | 5.x controls; Access controls; Monitoring (8.16); Secure Development Life Cycle (8.25) | Secure coding principles shall be applied to software development | Documents | Proof of secure code review, secure code review training for development team.
8.29 | Security testing in development and acceptance | Technology | 3 | 5.x controls; Access controls; Monitoring (8.16); Secure Development Life Cycle (8.25) | Security testing processes shall be defined and implemented in the development life cycle | Documents | Proof of secure code testing in the QA, UAT stage of SDLC.
8.30 | Outsourced development | Technology | 4 | 5.x controls; Access controls; Monitoring (8.16) | The organization shall direct supervise and monitor the activities related to outsourced system development | Documents | Signed SoW with Outsource team that requires them to adhear to the SDLC Sec Dev policy, internal QA and UAT testing to verify.
8.31 | Separation of development test and production environments | Technology | 2 | 5.x controls; Access controls; Monitoring (8.16) | Development test and production environments shall be separated and secured | Documents | Separate Dev, QA/UAT, and Prod Git environments. Show architectural diagram.
8.32 | Change management | Technology | 4 | 5.x controls; Access controls; Monitoring (8.16) | Changes to information processing facilities and information systems shall be subject to change management procedures | Documents | SDLC Tickets with approver listed.
8.33 | Test information | Technology | 4 | 5.x controls; Access controls; Monitoring (8.16) | Test information shall be appropriately selected, protected, and managed | Documents | Process and Procedure Documents, SS of Test database access.
8.34 | Protection of information systems during audit testing | Technology | 3 | 5.x controls; Access controls; Monitoring (8.16) | Audit tests and other assurance activities involving assessment of operational systems shall be planned and agreed between the tester and appropriate management | Documents | Quartley checklists of the testing and auditing of relivant controls.

## Controls Sample
Control ID | Control Name | Category | Difficulty | Prerequisites | Control Description | Artifacts{Documents, Logs, Diagrams, Images, Video} | Sample
5.1 | Policies for information security | Organizational | 2 | None - Foundational | Information security policy and topic-specific policies shall be defined approved by management published communicated to and acknowledged by relevant personnel and relevant interested parties and reviewed at planned intervals and if significant changes occur | Documents | 5-1_information_security_policy.docx
5.2 | Information security roles and responsibilities | Organizational | 2 | None - Foundational | Information security roles and responsibilities shall be defined and allocated according to the organization needs | Documents, Diagrams | 5-2_Org_Chart.pdf
5.9 | Inventory of information and other associated assets | Organizational | P | 5.1 (Policy); 5.2 (Roles) | An inventory of information and other associated assets including owners shall be developed and maintained | Documents | Panteha generating.
5.11 | Return of assets | Organizational | P | 5.1 (Policy); 5.2 (Roles) | Personnel and other interested parties as appropriate shall return all the organization's assets in their possession upon change or termination of their employment contract or agreement | Documents, Logs | Panteha generating.
5.27 | Learning from information security incidents | Organizational | 1 | 5.1 (Policy); 5.2 (Roles) | Knowledge gained from information security incidents shall be used to strengthen and improve the information security controls | Documents | 5-27_incident_response_report.docx
5.29 | Information security during disruption | Organizational | 1 | 5.1 (Policy); 5.2 (Roles) | The organization shall plan how to maintain information security at an appropriate level during disruption | Documents
5.31 | Legal and contractual requirements | Organizational | 4 | 5.1 (Policy); 5.2 (Roles) | Legal statutory regulatory and contractual requirements relevant to information security and the organization's approach to meet these requirements shall be identified documented and kept up to date | Documents
7.10 | Storage media | Physical | P | 5.x controls; Asset management (5.9) | Storage media shall be managed through their life cycle of acquisition use transport and disposal in accordance with the organization's classification scheme and handling requirements | Documents, Images | Panteha generating.
7.14 | Secure disposal or re-use of equipment | Physical | P | 5.x controls; Asset management (5.9) | Items of equipment containing storage media shall be verified to ensure that any sensitive data and licensed software has been removed or securely overwritten prior to disposal or re-use | Documents | Panteha generating.

## Implementation Phases
Phase | Control ID | Control Name | Rationale
Phase 1 - Foundation | 5.1 | Policies for information security | Essential policies and organizational structure
Phase 1 - Foundation | 5.2 | Information security roles and responsibilities | Essential policies and organizational structure
Phase 2 - Organizational Structure | 5.3 | Segregation of duties | Sequential implementation based on dependencies
Phase 2 - Organizational Structure | 5.4 | Management responsibilities | Sequential implementation based on dependencies
Phase 2 - Organizational Structure | 5.5 | Contact with authorities | Sequential implementation based on dependencies
Phase 2 - Organizational Structure | 5.6 | Contact with special interest groups | Sequential implementation based on dependencies
Phase 2 - Organizational Structure | 5.7 | Threat intelligence | Sequential implementation based on dependencies
Phase 2 - Organizational Structure | 5.8 | Information security in project management | Sequential implementation based on dependencies
Phase 3 - Asset Management | 5.9 | Inventory of information and other associated assets | Requires policies from Phase 1-2
Phase 3 - Asset Management | 5.10 | Acceptable use of information and other associated assets | Requires policies from Phase 1-2
Phase 3 - Asset Management | 5.11 | Return of assets | Requires policies from Phase 1-2
Phase 3 - Asset Management | 5.12 | Classification of information | Requires policies from Phase 1-2
Phase 3 - Asset Management | 5.13 | Labelling of information | Requires policies from Phase 1-2
Phase 3 - Asset Management | 5.14 | Information transfer | Requires policies from Phase 1-2
Phase 4 - Access Control Foundation | 5.15 | Access control | Essential policies and organizational structure
Phase 4 - Access Control Foundation | 5.16 | Identity management | Essential policies and organizational structure
Phase 4 - Access Control Foundation | 5.17 | Authentication information | Essential policies and organizational structure
Phase 4 - Access Control Foundation | 5.18 | Access rights | Essential policies and organizational structure
Phase 5 - Operational Controls | 5.19 | Information security in supplier relationships | Sequential implementation based on dependencies
Phase 5 - Operational Controls | 5.20 | Addressing information security within supplier agreements | Sequential implementation based on dependencies
Phase 5 - Operational Controls | 5.21 | Managing information security in the ICT supply chain | Sequential implementation based on dependencies
Phase 5 - Operational Controls | 5.22 | Monitoring review and change management of supplier services | Sequential implementation based on dependencies
Phase 5 - Operational Controls | 5.23 | Information security for use of cloud services | Sequential implementation based on dependencies
Phase 6 - Incident Management | 5.24 | Information security incident management planning and preparation | Sequential implementation based on dependencies
Phase 6 - Incident Management | 5.25 | Assessment and decision on information security events | Sequential implementation based on dependencies
Phase 6 - Incident Management | 5.26 | Response to information security incidents | Sequential implementation based on dependencies
Phase 6 - Incident Management | 5.27 | Learning from information security incidents | Sequential implementation based on dependencies
Phase 6 - Incident Management | 5.28 | Collection of evidence | Sequential implementation based on dependencies
Phase 7 - Business Continuity | 5.29 | Information security during disruption | Sequential implementation based on dependencies
Phase 7 - Business Continuity | 5.30 | ICT readiness for business continuity | Sequential implementation based on dependencies
Phase 7 - Business Continuity | 5.31 | Legal and contractual requirements | Sequential implementation based on dependencies
Phase 8 - Compliance & Documentation | 5.32 | Intellectual property rights | Sequential implementation based on dependencies
Phase 8 - Compliance & Documentation | 5.33 | Protection of records | Sequential implementation based on dependencies
Phase 8 - Compliance & Documentation | 5.34 | Privacy and protection of personal information | Sequential implementation based on dependencies
Phase 8 - Compliance & Documentation | 5.35 | Independent review of information security | Sequential implementation based on dependencies
Phase 8 - Compliance & Documentation | 5.36 | Compliance with policies and standards for information security | Sequential implementation based on dependencies
Phase 8 - Compliance & Documentation | 5.37 | Documented operating procedures | Sequential implementation based on dependencies
Phase 9 - People Controls | 6.1 | Screening | Requires access controls and policies
Phase 9 - People Controls | 6.2 | Terms and conditions of employment | Requires access controls and policies
Phase 9 - People Controls | 6.3 | Information security awareness education and training | Requires access controls and policies
Phase 9 - People Controls | 6.4 | Disciplinary process | Requires access controls and policies
Phase 9 - People Controls | 6.5 | Responsibilities after termination or change of employment | Requires access controls and policies
Phase 9 - People Controls | 6.6 | Confidentiality or non-disclosure agreements | Requires access controls and policies
Phase 9 - People Controls | 6.7 | Remote working | Requires access controls and policies
Phase 9 - People Controls | 6.8 | Information security event reporting | Requires access controls and policies
Phase 10 - Physical Security | 7.1 | Physical security perimeters | Requires asset management and access controls
Phase 10 - Physical Security | 7.2 | Physical entry | Requires asset management and access controls
Phase 10 - Physical Security | 7.3 | Securing offices rooms and facilities | Requires asset management and access controls
Phase 10 - Physical Security | 7.4 | Physical security monitoring | Requires asset management and access controls
Phase 10 - Physical Security | 7.5 | Protecting against physical and environmental threats | Requires asset management and access controls
Phase 10 - Physical Security | 7.6 | Working in secure areas | Requires asset management and access controls
Phase 10 - Physical Security | 7.7 | Clear desk and clear screen | Requires asset management and access controls
Phase 10 - Physical Security | 7.8 | Equipment siting and protection | Requires asset management and access controls
Phase 10 - Physical Security | 7.9 | Security of assets off-premises | Requires asset management and access controls
Phase 10 - Physical Security | 7.10 | Storage media | Requires asset management and access controls
Phase 10 - Physical Security | 7.11 | Supporting utilities | Requires asset management and access controls
Phase 10 - Physical Security | 7.12 | Cabling security | Requires asset management and access controls
Phase 10 - Physical Security | 7.13 | Equipment maintenance | Requires asset management and access controls
Phase 10 - Physical Security | 7.14 | Secure disposal or re-use of equipment | Requires asset management and access controls
Phase 11 - Technology Controls Foundation | 8.1 | User endpoint devices | Essential policies and organizational structure
Phase 11 - Technology Controls Foundation | 8.2 | Privileged access rights | Essential policies and organizational structure
Phase 11 - Technology Controls Foundation | 8.15 | Logging | Essential policies and organizational structure
Phase 11 - Technology Controls Foundation | 8.16 | Monitoring activities | Essential policies and organizational structure
Phase 11 - Technology Controls Foundation | 8.17 | Clock synchronization | Essential policies and organizational structure
Phase 11 - Technology Controls Foundation | 8.20 | Networks security | Essential policies and organizational structure
Phase 12 - Advanced Technology Controls | 8.3 | Information access restriction | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.4 | Access to source code | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.5 | Secure authentication | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.6 | Capacity management | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.7 | Protection against malware | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.8 | Management of technical vulnerabilities | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.9 | Configuration management | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.10 | Information deletion | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.11 | Data masking | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.12 | Data leakage prevention | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.13 | Information backup | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.14 | Redundancy of information processing facilities | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.18 | Use of privileged utility programs | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.19 | Installation of software on operational systems | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.21 | Security of network services | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.22 | Segregation of networks | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.23 | Web filtering | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.24 | Use of cryptography | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.25 | Secure development life cycle | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.26 | Application security requirements | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.27 | Secure system architecture and engineering principles | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.28 | Secure coding | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.29 | Security testing in development and acceptance | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.30 | Outsourced development | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.31 | Separation of development test and production environments | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.32 | Change management | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.33 | Test information | Requires all foundational controls
Phase 12 - Advanced Technology Controls | 8.34 | Protection of information systems during audit testing | Requires all foundational controls

## Dependency Matrix
| 5.1 | 5.2 | 5.3 | 5.4 | 5.5 | 5.6 | 5.7 | 5.8 | 5.9 | 5.10 | 5.11 | 5.12 | 5.13 | 5.14 | 5.15 | 5.16 | 5.17 | 5.18 | 5.19 | 5.20 | 5.21 | 5.22 | 5.23 | 5.24 | 5.25 | 5.26 | 5.27 | 5.28 | 5.29 | 5.30 | 5.31 | 5.32 | 5.33 | 5.34 | 5.35 | 5.36 | 5.37 | 6.1 | 6.2 | 6.3 | 6.4 | 6.5 | 6.6 | 6.7 | 6.8 | 7.1 | 7.2 | 7.3 | 7.4 | 7.5 | 7.6 | 7.7 | 7.8 | 7.9 | 7.10 | 7.11 | 7.12 | 7.13 | 7.14 | 8.1 | 8.2 | 8.3 | 8.4 | 8.5 | 8.6 | 8.7 | 8.8 | 8.9 | 8.10 | 8.11 | 8.12 | 8.13 | 8.14 | 8.15 | 8.16 | 8.17 | 8.18 | 8.19 | 8.20 | 8.21 | 8.22 | 8.23 | 8.24 | 8.25 | 8.26 | 8.27 | 8.28 | 8.29 | 8.30 | 8.31 | 8.32 | 8.33 | 8.34
5.1
5.2 | bar: 5.1
5.3 | bar: 5.2
5.4 | bar: 5.1
5.5
5.6
5.7
5.8
5.9 | bar: 5.1
5.10
5.11
5.12 | bar: 5.1
5.13 | bar: 5.12
5.14
5.15 | bar: 5.1; 5.9
5.16 | bar: 5.1
5.17 | bar: 5.1
5.18 | bar: 5.1 to 5.2
5.19
5.20
5.21
5.22
5.23
5.24
5.25
5.26
5.27
5.28
5.29
5.30
5.31
5.32
5.33
5.34
5.35
5.36
5.37
6.1
6.2
6.3
6.4
6.5
6.6
6.7
6.8
7.1
7.2
7.3
7.4
7.5
7.6
7.7
7.8
7.9
7.10
7.11
7.12
7.13
7.14
8.1
8.2
8.3
8.4
8.5
8.6
8.7
8.8
8.9
8.10
8.11
8.12
8.13
8.14
8.15
8.16 | bar: 5.1
8.17
8.18
8.19
8.20 | bar: 8.16
8.21
8.22
8.23
8.24
8.25 | bar: 5.1
8.26
8.27
8.28
8.29
8.30
8.31
8.32
8.33
8.34

## Critical Path Analysis
Level | Controls | Description | Success Criteria
Level 1 - Foundation | 5.1, 5.2 | Establish information security policy and define roles/responsibilities | Approved policies, defined security roles, management commitment
Level 2 - Governance | 5.3, 5.4, 5.8 | Implement governance structure and management oversight | Segregation controls, management processes, project security integration
Level 3 - Asset Management | 5.9, 5.10, 5.11, 5.12 | Identify, classify, and manage information assets | Complete asset inventory, classification scheme, asset handling procedures
Level 4 - Access Foundation | 5.15, 5.16, 5.17, 5.18 | Establish access control framework and identity management | Access control policy, identity lifecycle, authentication systems
Level 5 - People & Physical | 6.x, 7.x | Implement people security and physical controls | HR security processes, physical security perimeters, training programs
Level 6 - Technology Controls | 8.x | Deploy technical security controls and monitoring | Security monitoring, network controls, secure development practices